## Agile Product Backlog
AGILE PRODUCT BACKLOG TEMPLATE | Scrum Meeting Task
TASK ID | TASK NAME | SPRINT # | ASSIGNED TO | START | FINISH | STORY | SPRINT READY | PRIORITY | STATUS | STORY POINTS | ASSIGNED TO SPRINT
|  | Sprint 1 | C. Jones | 2022-07-05 |  | No | No | High | In Progress | 24 | No
| First Group Meeting | " getting to know each and upload our project from previous group adding group to discord for communication " | "Abebew, Bree, Stella, Bradlee, Kiros " | 2022-02-05 | 2020-02-18 | Yes | Yes | Medium | Complete | 8 | Yes | This section is for the drop-down list
| Second Group Meeting | "Discussing each our projects and what we liked about our project " | "Abebew, Bree, Stella, Bradlee, Kiros " | 2022-02-12 | 2020-02-12 | Yes | Yes | Medium | Complete | 16 | Yes | Yes | High | Complete
| Third Group Meeting | " Decide on which project to work off from "Bree and Bradlee were chosen" | "Abebew, Bree, Stella, Bradlee, Kiros " | 2020-02-18 | 2020-02-19 | Yes | Yes | Medium | Complete | 0 | Yes | No | Medium | In Progress
|  | Sprint 2 | [10 empty] | Low | Not Started
| Four Group Meeting(Stella couldn't make it) | Merging of the two project with Bree and Bradlee project. | Abebew, Bree, Bradlee, Kiros | 2020-02-18 | 2020-02-18 | NO | Yes | High | complete |  | Yes
| Graph | trying to add the graph into Bradlee Gui | Bree, Abebew and Bradlee | 2020-02-19 | 2020-02-29 | NO | Yes | High | complete |  | Yes
| Graph and Gui | creating a new GUI as default to add the features we wanted into it. | Bree and Bradlee |  |  | NO | Yes | Medium | complete |  | Yes
Sprint 3
| Project Backlog | creating the Project backLog Discord Group call meeting to discuss code and what to implement | Bree and Stella(backlog) everyone else included in the meeting. | 2020-02-17 | 2020-02-18 | NO | Yes | Medium | complete |  | Yes
| Scrum meeting | created the scrum meeting log | Stella | 2020-02-18 | 2020-02-18 | No | Yes | Medium | complete |  | Yes
| Fifth Group Meeting | Group meeting to review requirements and transfer compass over to project file | Bree and bradle after the meeting everyone else. | 2020-02-26 | 2020-02-26 | No | Yes | High | complete |  | Yes
Sprint 4
| final Product | testing and Junit testing for functionalization of the software | Bree | 2020-02-29 | 2020-03-01 | No | Yes | High | complete |  | Yes
| Github | upload to group github (folder of the software, | Stella | 2020-03-01 | 2020-03-01 | No | Yes | High | complete |  | Yes
| Scrum Meeting | finishing the last of the meeting requirements and sending it to github and canvas | stella | 2020-03-01 | 2020-03-01 | No | Yes | High | complete |  | Yes

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.